## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | M1-1 | 1.Choose the data either small, medium or large text data | MUST HAVE | -- |  | 3- Completed
1 | 1 | M1-2 | 2.Read the data file | MUST HAVE | M1-1 |  | 3- Completed
1 | 1 | M1-3 | 3.Store the data in the database and fetch the data | MUST HAVE | M1-2 |  | 3- Completed
1 | 1 | M1-4 | 4.Do text cleaning and normalization | MUST HAVE | M1-3 |  | 3- Completed
1 | 1 | M1-5 | 5.Using multiprocessing techniques, find the word and its counts. | MUST HAVE | M1-4 |  | 3- Completed
2 | 2 | M2-1 | 1.Load the Dataset and Prepare the Environment | MUST HAVE |  |  | 3- Completed
2 | 2 | M2-2 | 2.Store Raw Data in the Database | MUST HAVE | M2-1 |  | 3- Completed
2 | 2 | M2-3 | 3.Perform Parallel Sentiment Analysis | MUST HAVE | M2-2 |  | 3- Completed
2 | 2 | M2-4 | 4.Generate and Store the Analysis Summary | MUST HAVE | M2-2 |  | 3- Completed
2 | 2 | M2-5 | 5.Automate Reporting via Email | MUST HAVE |  |  | 3- Completed
3 | 3 | M3-1 | 1.Prepare the 1000-review subset and map star ratings to 'Positive', 'Neutral', 'Negative' ground truth labels | MUST HAVE | M2-5 |  | 3- Completed
3 | 3 | M3-2 | 2. Implement and execute VADER sentiment analysis in both sequential and parallel (multiprocessing) modes. | MUST HAVE | M3-1 |  | 3- Completed
3 | 3 | M3-3 | 3. Implement and execute Hugging Face (RoBERTa) sentiment analysis in both sequential and parallel (threading) modes | MUST HAVE | M3-1 |  | 3- Completed
3 | 3 | M3-4 | 4. Evaluate and compare the accuracy, runtime performance, and confusion matrices for both VADER and RoBERTa models | MUST HAVE | M3-2, M3-3 |  | 3- Completed
3 | 3 | M3-5 | 5. Automate reporting by creating a function to email the final analysis CSV as an attachment. | MUST HAVE | M3-4 |  | 3- Completed
4 | 4 | M4-1 | 1. Design and build the main application UI with sidebar navigation. | MUST HAVE | -- |  | 3- Completed
4 | 4 | M4-2 | 2. Create the "VADER Analysis" page with text/file inputs and output cards for stats, preview, graph (Chart.js), and top words. | MUST HAVE | M4-1, M3-2 |  | 3- Completed
4 | 4 | M4-3 | 3. Create the "Hugging Face" page with identical inputs/outputs for the RoBERTa model. | MUST HAVE | M4-1, M3-3 |  | 3- Completed
4 | 4 | M4-4 | 4. Implement the "VADER vs. HF" page to fetch stored results and display a comparison table and a grouped bar chart (Chart.js). | MUST HAVE | M4-2, M4-3 |  | 3- Completed
4 | 4 | M4-5 | 5. Implement the "Top Words" page with inputs to call the dedicated NLTK endpoint. | MUST HAVE | M4-1, M3-3 |  | 3- Completed
4 | 4 | M4-6 | 6. Implement the "Database & Download" page with a functional "Download Results" button, "Email Results" (mailto:) button, and a placeholder for the database feature. | MUST HAVE | M4-2, M4-3 |  | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
M-1 | 1 | Selected and read the text review dataset from a CSV file. Established the initial SQLite database schema and stored the raw text data. Performed essential text cleaning (like lowercasing) and normalization (like tokenization). Implemented a multiprocessing function to efficiently find and count all word frequencies in the dataset. | 2025-09-09 | 2025-09-16 | vikas | Coding | 3- Completed
M-2 | 2 | Prepared the full environment and loaded the dataset for the analysis pipeline. Stored the raw data in the database in preparation for processing. Implemented the first sentiment analysis model and ran it in parallel across the dataset. Generated and stored the aggregated summary of sentiment results and automated the email reporting | 2025-09-24 | 2025-10-06 | vikas | Coding | 3- Completed
M-3 | 3 | Created a 1000-review "ground truth" subset by mapping star ratings to Positive, Negative, or Neutral labels. Implemented VADER analysis in both sequential and parallel (multiprocessing) modes to compare performance. Implemented Hugging Face (RoBERTa) analysis in sequential and parallel (threading) modes. Evaluated both VADER and RoBERTa for accuracy against the ground truth and created a function to email the final comparison. | 2025-10-09 | 2025-10-17 | vikas | Coding | 3- Completed
M-4 | 4 | 1.Built a full-stack, multi-page web application with a FastAPI backend and a JavaScript-driven sidebar navigation. 2.Created dedicated UI pages for VADER and Hugging Face, each handling text/file uploads and displaying results (stats, preview, Chart.js graphs). 3.Engineered a "Top Words" feature using NLTK (tokenization, stop-word removal) and integrated it into the analysis pages and its own dedicated page. 4.Developed a "VADER vs. HF" comparison dashboard with a detailed table and grouped bar chart, plus functional "Download (CSV)" and "Email Results" buttons. | 2025-10-17 | 2025-10-28 | vikas | Coding | 3-completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2025-09-09 | Multiprocessing | Done
1 | 2025-09-10 | Choose sqlite as database and dataset | Completed sucessfully
1 | 2025-09-16 | Milestone one presentation | Done
1 | 2025-09-17 | Finalze the code and submited | Submitted the final code
2 | 2025-09-24 | Discussed on email alerts | explore how to send email alerts
2 | 2025-09-26 | Discussed TF vectorization | Implemented TF vectorization code
2 | 2025-09-30 | Discussed tasks should be done in milestone2 | Code is started for milestone2
2 | 2025-10-03 | Milestone-2 code assigned to mentor | Code reviewed
2 | 2025-10-04 | Made changes in code | updated the code
2 | 2025-10-06 | Milestone-2 code submitted and discussed about milestone-3 | Milestone-2 code submitted
3 | 2025-10-09 | Discussed tasks to be done in milestone 3 | Started working on milestone 3
3 | 2025-10-10 | Started working on milestone 3 and clarified doubts | Coding part has started
3 | 2025-10-13 | presenting milestone 3 | working on code
3 | 2025-10-14 | Presentation of milestone 3 | working on errors
3 | 2025-10-15 | Presented project code | working on errors
3 | 2025-10-16 | project presenataion | project presentation
3 | 2025-10-16 | discussed about project UI | Started working on UI code
3 | 2025-10-17 | project presenataion and disscussed about ui part | updated the UI code
4 | 2025-10-22 | Developed UI code | working on code
4 | 2025-10-23 | presented code ui code | worked on errors
4 | 2025-10-24 | disscused about UI features | added more features
4 | 2025-10-27 | presented developed UI code | UI code done
4 | 2025-10-30 | disscused about ppt | started working ppt

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-08 | 2025-09-16 | Vikas | Started on processing text and worked on task for milestone one | Completed all tasks for milestone | no | Completed all tasks
2 | 2 | 2025-09-24 | 2025-10-06 | Vikas | Started on sending email alerts and TF vectorization | Stopped by implementing sentiment analysis on datset | no | Completed all tasks
3 | 3 | 2025-10-09 | 2025-10-17 | vikas | Started working on vader and hugging face for sentiment analysis | Stopped by implementing sentiment analysis on datset | no | Completed all tasks
4 | 4 | 2025-10-17 | 2025-10-28 | vikas | Started working on UI part | Stopped by Developing UI part | no | Completed all tasks
5
6
7